## Slide 1
Fundamentals of Monitoring and Evaluation
Tool 7
Activity C.2
Integrating Gender in the Monitoring and Evaluation of Health Programs:
A Toolkit

## Slide 2
Define monitoring and evaluation (M&E)
Review the purpose of M&E
Explore how M&E fits in the program life cycle
Describe the components of M&E plans
Learning Objectives
Notes: The learning objectives for this session are (read slide)

## Slide 3
What is monitoring?
What is evaluation?
How are they different?
How do they fit together?
Activity
Brainstorming
Notes: This activity is meant to help clarify M&E concepts. Ask participants to come up with a list of what monitoring is. Then ask participants to come up with a list of what evaluation is. Lead the group by asking them to shout out what words come to mind when they think of monitoring and when they think of evaluation. You can use a flip chart to organize the ideas in two columns: “What is monitoring?” and “What is evaluation?”
Next, lead a discussion of how the two terms are different:
How are they different?
How do they fit together?
Source: Gage, A.J., & Dunn, M. (2010). Module II: Monitoring and evaluating gender-based violence prevention and mitigation programs: A facilitator’s training guide. Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from https://www.measureevaluation.org/resources/training/capacity-building-resources/gbv.

## Slide 4
Key Points
Monitoring
Ongoing
Continuous process
Data collection at multiple points throughout a program
Tracking changes over time
Evaluation
Is not continuous
Data collection at the start and end of a program
Control/comparison group
Well-planned study design
Notes: Be sure that the following points are discussed:
Monitoring is an ongoing, continuous process; it requires data collection at multiple points throughout the program cycle, including at the beginning to provide a baseline; and monitoring means tracking changes over time.
Evaluation measures how well the program activities have met expected objectives, and attributes changes in outcomes to the program or intervention. Evaluation requires data collection at the start of the program to provide a baseline, and again at the end, rather than at repeated intervals during program implementation. It also requires a control or comparison group, and a well-planned study design.
Source: Gage, A.J., Dunn, M. (2010). Module II: Monitoring and evaluating gender-based violence prevention and mitigation programs: A facilitator’s training guide. Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from https://www.measureevaluation.org/resources/training/capacity-building-resources/gbv.

## Slide 5
Performance monitoring reveals whether desired results are occurring and whether implementation is on track. In general, the results measured are the direct and near-term consequences of project activities.
  Performance monitoring is used to gauge whether activities need adjustment in the course of the intervention to improve the use of resources and the achievement of desired outcomes.
  It requires the collection of data at multiple points throughout the program cycle, including at the beginning to provide a baseline.
Definition
Monitoring
Notes: There are different definitions of monitoring. For performance monitoring, some measure the process of program implementation (e.g., is the program doing what is expected regarding its activities and outputs?) and some focus on outcome monitoring (e.g., has the program done what was expected regarding its expected outcomes?).

## Slide 6
Evaluation is the systematic collection and analysis of information about the characteristics and outcomes of a program or project as a basis for judgments, to improve effectiveness, and/or to inform decisions about current and future programming.
Evaluation is distinct from assessment, which may be designed to examine country or sector context to inform project design or an informal review of a project.
Definition
Evaluation
Notes: Source: USAID. (2016). USAID evaluation policy. Washington, DC, USA: USAID. Retrieved from https://www.usaid.gov/sites/default/files/documents/1870/USAIDEvaluationPolicy.pdf

## Slide 7
Performance evaluation focuses on descriptive and normative questions: what has a particular project or program achieved; how it is being implemented; how is it perceived and valued; are expected results occurring; and other questions that are pertinent to program design, management, and operational decision making.
Performance evaluations often incorporate before-after comparisons, but generally lack a rigorously defined counterfactual.
They involve the collection of data at the start of a program (to provide a baseline) and again at the end.
Types of Evaluations
Notes: There are different definitions of evaluation. For performance evaluation, some call it process evaluation (e.g., addressing program operations, namely the who, what, when, and how many of program activities and program outputs) or outcome evaluation (e.g., are the outcomes attributable to the intervention?).

## Slide 8
Impact evaluation measures the change in a development outcome that is attributable to a defined intervention; impact evaluations are based on models of cause and effect and require a credible and rigorously defined counterfactual to control for factors other than the intervention that might account for the observed change.
Impact evaluations in which comparisons are made between beneficiaries that are randomly assigned to either a treatment or a control group provide the strongest evidence of a relationship between the intervention under study and the outcomes measured.
Types of Evaluations

## Slide 9
M&E provide objective evidence to inform decision making.
M&E ensure the most effective and efficient use of resources.
M&E objectively assess the extent to which a program is having or has had the desired impact, in what areas it is effective, and where corrections need to be considered.
M&E produce information that can help convince donors that their investments have been worthwhile or that alternative approaches should be considered.
Why is M&E Important?
Notes: Source: Frankel, N., & Gage, A. (2007, rev. 2016). M&E fundamentals: A self-guided minicourse (MS-07-20_rev2016.pdf). Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from http://www.cpc.unc.edu/measure/publications/ms-07-20.

## Slide 10
M&E are continuous processes that occur throughout the life of a program.
To be most effective, M&E should be planned at the design stage.
Monitoring should be conducted at every stage of the program, with data collected, analyzed, and used on a continuous basis.
Evaluations are usually conducted at the end of programs. However, they should be planned at the start because baseline data are important for end-of-program comparisons.
When should M&E take place?
Notes: The required time, money, and personnel to conduct M&E effectively should be budgeted at the beginning of the program life cycle.
Source: Frankel, N., & Gage, A. (2007, rev. 2016). M&E fundamentals: A self-guided minicourse (MS-07-20_rev2016.pdf). Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from http://www.cpc.unc.edu/measure/publications/ms-07-20.

## Slide 11
An M&E plan is a fundamental document that describes:
  A program’s objectives.
  The interventions developed to achieve these objectives.
  The activities that will determine whether or not the objectives are met.
  How the expected results of a program relate to its goals and objectives.
  The data needed and how the data will be collected, analyzed, and used.
  The resources required to conduct the plan.
  How the program will be accountable to stakeholders.
What is an M&E Plan?

## Slide 12
M&E plans can be organized in a variety of ways. The plan typically includes:
  Underlying assumptions
  Anticipated relationships
  Measures and definitions
  Monitoring schedule
  Data sources
  Cost estimates
  List of partnerships and collaborations
  A plan for dissemination and use of information gained
What makes an M&E Plan?
Notes: The underlying assumptions on which the achievement of program goals depend.
The anticipated relationships among activities, outputs, and outcomes.
Well-defined conceptual measures and definitions, along with baseline values.
The monitoring schedule.
A list of data sources to be used.
Cost estimates for the M&E activities.
A list of the partnerships and collaborations that will help achieve the desired results.
A plan for the dissemination and use of the information gained.

## Slide 13
Monitoring & Evaluation
References & Resources
Gage, A.J., & Dunn, M. (2010). Module II: Monitoring and evaluating gender-based violence prevention and mitigation programs: a facilitator’s training guide. Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from https://www.measureevaluation.org/resources/training/capacity-building-resources/gbv.
Frankel, N., & Gage, A. (2007, rev. 2016). M&E fundamentals: a self-guided minicourse MS-07-20_rev2016.pdf). Chapel Hill, NC, USA: MEASURE Evaluation, University of North Carolina. Retrieved from http://www.cpc.unc.edu/measure/publications/ms-07-20.
Frankel, N., & Gage, A. (2006). Global Health eLearning Center course on M&E fundamentals. Retrieved from http://www.globalhealthlearning.org/course/m-e-fundamentals.

## Slide 14
Monitoring & Evaluation
References & Resources
Social Impact, Inc. (2013). Performance management plan (PMP) toolkit. A guide for Missions on planning for, developing, updating, and actively using a PMP. Washington, DC, USA: Social Impact, Inc. Retrieved from http://usaidprojectstarter.org/sites/default/files/resources/pdfs/PMP-Toolkit.pdf.
Measurement, Learning & Evaluation Project. (2013). Measuring success toolkit: sample outline of an M&E plan. Retrieved from https://www.urbanreproductivehealth.org/toolkits/measuring-success/sample-outline-me-plan.
USAID. (2016). USAID evaluation policy. Washington, DC, USA: USAID. Retrieved from https://www.usaid.gov/sites/default/files/documents/1870/USAIDEvaluationPolicy.pdf.

## Slide 15
This presentation was produced with the support of the United States Agency for International Development (USAID) under the terms of MEASURE Evaluation cooperative agreement AID-OAA-L-14-00004. MEASURE Evaluation is implemented by the Carolina Population Center, University of North Carolina at Chapel Hill in partnership with ICF International; John Snow, Inc.; Management Sciences for Health; Palladium; and Tulane University. Views expressed are not necessarily those of USAID or the United States government.
www.measureevaluation.org